## Sheet1
Risk | Probability | Impact | Risk
Failure to integrate Chat and Feed features | 0.8 | 0.4 | 0.32
User data leakage due to improper encryption | 0.6 | 0.8 | 0.48 |  | Almost Certain
Incompatibility of the webapp on older browser versions or different browsers | 0.8 | 0.4 | 0.32 |  | Likely
Addition of unplanned features during development | 0.6 | 0.2 | 0.12 |  | Moderate
Insufficient funds for additional testing phases | 0.6 | 0.8 | 0.48 |  | Unlikely
Inadequate team skills in implementing XP process model | 0.4 | 0.8 | 0.32 |  | Rare
Users unable to understand UI | 0.2 | 0.4 | 0.08 |  |  | Insignificant | Minor | Moderate | Major | Catastrophic
Failure to implement responsive design for mobile users | 0.4 | 0.4 | 0.16
Negative reviews about the platform’s accessibility (disabled users) | 0.4 | 0.8 | 0.32
Server downtime or failures when high traffic | 0.4 | 0.4 | 0.16
poor moderation or monitoring post launch | 0.2 | 0.4 | 0.08 | 0.8 | Almost Certain
poor performance of search or filter due to unoptimized algorithm | 0.4 | 0.4 | 0.16 | 0.6 | Likely
Lack of proper backup of user data | 0.2 | 0.8 | 0.16 | 0.4 | Moderate
depending on outdated libraries that don't have support or updates | 0.2 | 0.8 | 0.16 | 0.2 | Unlikely
A competitor launching a similar platform with better features before your release | 0.6 | 0.8 | 0.48 | 0.1 | Rare
[6 empty] | Insignificant | Minor | Moderate | Major | Catastrophic
[6 empty] | 0.05 | 0.1 | 0.2 | 0.4 | 0.8